## Slide 2
Road to Prosperity
Roads And Bridges Development
Corporation of Kerala LTD
Project Review Meeting –
1st July 2015

## Slide 3: ONGOING PROJECTS
FLYOVER AT PALARIVATTOM
ROB AT ALOOR-MALA
ROB AT ANGADIPURAM
4. RIVER BRIDGES AT MAHILALAYAM-CHOWARA Seaport Airport Road Phase II Section B
5. ROB AT KUMARANALLOOR
6. ROB AT KUNHIPPALLY
7. ROB AT EROOR
8. ROB AT DIVINE NAGAR

## Slide 4: FLYOVER AT PALARIVATTOM

## Slide 5: PROGRESS STATUS
All substructure works completed
Girder casting (68/122) completed
20 girders launched; 6 on Edappally side and 14 on Vyttila side.
Service road on Edappally and Vyttila sides completed up to DBM.
Casting of precast drain started.

## Slide 6: WORKS DURING JUNE 2015
TARGETED
Pier – 1 no (P18)
Pier cap – 1 no (P18)
Girder casting – 15 nos
Girder Launching – 18 nos
Precast Drain – 200 m
Deck Slab – 2 nos
ACHIEVED
Pier – 1 no (P18)
Pier cap – 1 no (P18)
Girder casting – 18 nos
Girder Launching – 18 nos
Precast Drain – 62 m
Deck Slab – Zero

## Slide 7: PROGRESS GRAPH

## Slide 8: PROGRESS PHOTOS
Girder Concreting
Girder Launching
Launched Girders in AP1-P1 span
Casting of precast drain

## Slide 9: ROB AT ALOOR-MALA

## Slide 10: PROGRESS STATUS
All superstructure works and approach road completed except wearing coat of one adjacent span.
The balance works include painting, road marking, construction of staircases and toll booth.
Railway span is being executed by RAILWAYS. The parapet wall to be constructed.

## Slide 11: PROGRESS GRAPH

## Slide 12: PROGRESS PHOTOS
Expansion joint
CC Wearing coat in adj.span
Reinforcement for adj.span
Painting

## Slide 13: ROB AT ANGADIPURAM

## Slide 14: PROGRESS STATUS
Piling completed. Pile cap (13/18), Pier (11/18), Pier cap (9/18) and Girders (3/54) are completed.
45% of retaining wall and 40m drain completed on Angadipuram side.

## Slide 15: WORKS DURING JUNE 2015
TARGETED
Pier cap – 1 (P14)
Girder – 1 (P3-P4)
Deck Slab – 1 (P3-P4)
Retaining wall (Angadipuram side) – 100%
Service road (Perinthalmanna side) – 100%
Drain – 100m
Building Dismantling – 100%
ACHIEVED
Pier cap – 1 (P14)
Girder – 1 (P3-P4)
Deck Slab – Zero
Retaining wall (Angadipuram side) – 45%
Service road (Perinthalmanna side) – 0%
Drain – 40m
Building Dismantling – 95%

## Slide 16: PROGRESS GRAPH

## Slide 17: PROGRESS PHOTOS
Drain work on Angadipuram side
Building dismantling
Road repairing
Girder P3 – P4

## Slide 18: RIVER BRIDGES AT MAHILALAYAM-CHOWARA Seaport Airport Road Phase II Section B

## Slide 19: PROGRESS STATUS OF MAIN BRIDGE
All works up to Pier cap completed
Girders (40/48) casted and 36 girders launched
Deck slabs (6/12) casted.

## Slide 20: PROGRESS STATUS OF MINOR BRIDGE
Pile (13/17), Pile cap (4/5), Pier (4/5), Pier cap(4/5) and Girders (10/16) are completed.

## Slide 21: WORKS DURING JUNE 2015
TARGETED
Main Bridge
Girder – 4 nos (2 nos each in P1-P2& P2-P3)
Girder Launching – 8 nos (4 nos each in P2-P3 & P3-P4)
Deck Slab – 1 (P6-P7)
Minor Bridge
Girder – 2 nos(P2’-P3’)
ACHIEVED
Main Bridge
Girder – 3 nos (1 no in P1-P2& 2 nos in P2-P3)
Girder Launching – 4 nos (4 nos in P3-P4)
Deck Slab – 1 (P6-P7)
Minor Bridge
Girder – 1 no(P2’-P3’)

## Slide 22: PROGRESS GRAPH

## Slide 23: PROGRESS PHOTOS

## Slide 24: ROB AT KUMARANALLOOR

## Slide 25: PROGRESS STATUS
The ROB was inaugurated and opened to traffic on May 24,2015.
Construction of staircases and toll booth to be completed.

## Slide 26: ROB AT KUMARANELLUR

## Slide 27: ROB AT KUNHIPPALLY

## Slide 28: PROGRESS STATUS
All works up to pier cap completed
Out of 16 spans, girder and slab casting completed in 14 spans
Expansion joint and kerb works completed in 12 spans
Handrail work completed in 8 spans
Retaining wall on Monthal side completed
Retaining wall on NH side to be started. Here work can be completed only after getting possession of land owned by Late Dr. Irfan Habeeb.

## Slide 29: WORKS DURING JUNE 2015
TARGETED
Girder – 1 (Adjacent span on Monthal side)
Expansion joint – 3 nos
Handrail – 5 spans
Painting (P5-P6) – 30%
Drain (Monthal side) –Complete
Retaining Wall (Monthal side) – Complete
Dirt Wall – 2 nos (A1,A2)
ACHIEVED
Girder – Zero (Adjacent span on Monthal side)
Expansion joint – 3 nos
Handrail – 5 spans
Painting (P5-P6) – 20%
Drain (Monthal side) – 98%
Retaining Wall (Monthal side) – Complete
Dirt Wall – 1 no (A2)

## Slide 30: PROGRESS GRAPH

## Slide 31: PROGRESS PHOTOS
Diversion Road-Monthal side
Painting in Progress
Staging Work
Dirt Wall – A2

## Slide 32: ROB AT EROOR

## Slide 33: PROGRESS STATUS
Piling completed. Pile cap (7/10), Pier (4/10) and Pier cap (4/10) are completed.
Slab casting started and (1/10) is completed
Construction of service roads to be started

## Slide 34: WORKS DURING JUNE 2015
TARGETED
Pile – 7 nos (2 nos in P8 & P7, 3 nos in A2)
Pile cap – P5,P6,P7
Pier – P5,P6,P7
Drainage – 50 m
Span – 2 (P2-P3 & P1-P2)
ACHIEVED
Pile – 7 nos (2 nos in P8 & P7, 3 nos in A2)
Pile cap – P5,P6
Pier – Zero
Drainage – 50 m
Span – 1 (P2-P3)

## Slide 35: PROGRESS GRAPH

## Slide 36: PROGRESS PHOTOS
Pile Casting
Staging for P1-P2 span
Placing of Voids in span P2-P3
View from P2 – P3 span

## Slide 37: ROB AT DIVINE NAGAR

## Slide 38: ADJACENT SPANS OF DIVINE NAGAR ROB
Casting of Slab in adjacent span RP1-P6A completed
Handrail and Kerb works started in RP1-P6A span.
Setting out completed for constructing staircase at Divine Side
Works in adjacent span RP2-P7 to be started

## Slide 39: PROGRESS GRAPH

## Slide 40: ADJACENT SPAN RP1-P6A Kadukutty Side