## Progress report
Progress Report For Pulianam ROB for the week ending on 02.09.11
Sl No | Activity Description | Total Quantity | Cumulative progress upto last week | Balance work up to last week | Cumulative delay in Qty up to last week | Work planned during the week | Actual work done during the week | Cumulative delay in Qty up to this week | Work Planned for next week | Remarks
1 | Pile towards NH side | 26 | 26 | 0 | 0 | 1 | 1 | 0 | 0 | TARGET ACHIEVED
2 | Pile towards Puliyanam side | 18 | 14 | 4 | 0 | 4 | 4 | 0 | 3
3 | Pile cap at NH Side | 6 | 4 | 2 | 0 | 1 | 2 | 0 | 0
4 | Pile Cap at Pulianam side | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 1
5 | RC wall at Puliyanam side | 100% | 15% | 85% | 0 | 5% | 5% | 0 | 5%
6 | pier at NH side | 5 | 2 | 3 | 0 | 1 | 2 | 0 | 1
Date | 27.08.2011 | 29.08.2011 | 30.08.2011 | 31.08.2011 | 01.08.2011 | 02.08.2011
Climate | RAINY | PLEASANT | PLEASANT | rainy | RAINY | RAINY
No.of labours | 40 | 44 | 38 | 27 | 22 | 22
availability of material
materials | Required | Available
Fine aggregate(M3) | 6 | 15
Coarse aggregate(M3) | 10 | 30
Cement(BAG) | 200 | 540
Steel(TONN) | 2 | 40